Onboarding plan – Project Coordinator (Chi)

Location: Tempe HQ (on-site)

Manager: Tim Haitaian (with input from Jayson Roti, Jared Aiken, Kendra Ash)

Buddy/Mentors: Jared Aiken & Jayson Roti

Start Date: October 20, 2025

Purpose

Establish a disciplined coordination and documentation function that maps current workflows, removes work from senior leaders, and improves customer experience. Chi will document the “as-is” process, propose and pilot “to-be” improvements, and deliver a 6-month rebuild of the workflow to leadership’s satisfaction.

High-Level Outcomes & Dates

- Day 30 (Nov 19, 2025): Complete end-to-end documentation of the entire existing workflow (as-is), plus two handoffs executed: dust permits  Eva and sign ordering  Eva, each with a format SOP/checklist and confirmation of capability.

- Day 60 (Dec 19, 2025): Deliver a written gap analysis and change recommendations, with incremental changes implemented continuously (prioritized to reduce load on Jared/Jayson/Kendra). Present draft KPI/SLAs for enactment at Day 90.

- Day 90 (Jan 18, 2026): Launch the first/next iteration of the workflow (to-be v1). Enact agreed KPI/SLA set and begin monthly iteration cadence (every ~30 days) through Day 180.

- Day 180 (Apr 18, 2026): 6-month objective/bonus checkpoint: Chi is designing and running a rebuilt workflow that leadership (Tim, Kendra, Jared, Jayson) confirms simplifies work for stakeholders and improves customer experience.

Immediate Actions

Setup Recurring Meetings

- 1:1 with Manager: weekly for first 8 weeks, bi-weekly during month 3, monthly after

- 1:1 with Mentors: weekly for first 8 weeks, then as needed

- Stakeholder forum: bi-weekly 30 minute sync (Tim, Jayson, Jared, Kendra) to review blockers, decisions and trade-offs

- [Weekly 10 Email: line update email incl progress, decisions needed, blockers, upcoming pilots, risks] --- more of a weekly update email, maybe open question, how are we doing, progress, ideas etc

Schedule Intro Meetings (learn roles, touchpoints, and pain point)

- Jayson Roti (SWPPP/Temp Fence) - Done

- Kendra Ash (Contract Admin) - Done

- Dawn Wagner (WT & SW Billing, Pre-quals/ Files) - Started

- Kerin Reissig (PJ & RO Billing) - Done

- Jared Aiken (Estimating) - Done

- Rick Haitaian (Sales/Estimating) - Done

- Lacie Stevin (Sales) - Scheduled

- Brandon Stevin (Sales) - Scheduled

- Stephen Judd (Portable Toilets) – not scheduled

- Daniel Venegas (Water Trucks) - Done

- Kelley Kline (Sweeping) – not scheduled

- Wendy Byers (Roll-off) – Scheduled

- Tevin (Monday.com Contractor – Email Scheduled

Deliverable: A one-page summary after each intro: current responsibilities, how work enters/exits their world, top 3 pain points, top 3 opportunities.

30/60/90 Expectations

Days 0-30 — "Learn & Document"

Objectives

- Map the entire current workflow for each service family (lead, quote, setup, execute, bill, collect)

- SOPs to ensure clarity on how the process works today

Deliverables

- Workflow Maps V0— swimlane diagrams + RACI for each major phase.

- Role Summaries of Intro Meetings

- SOPs (As-Is) for existing processes:

  - One Page SOP Template (Purpose, When, Steps, Inputs/Outputs, Owner, Files)

  - Intake & project setup

  - Handoffs to execution systems (SWPPP Master, CRO, Dawn's file)

  - Change requests (frequency, units, routing)

  - Closeout/archiving

- Dust Permit Process Draft (Jared to Eva): SOP + training checklist; Eva confirms readiness

- Sign Ordering Process Draft (Kerin to Eva): SOP + ordering matrix (vendor, lead times, sizes) + training checklist; Eva confirms readiness

- Pre-Qualification Process (Draft) incl. training checklist — define the formal process flow with Dawn: triggers, packet contents (safety, insurance, W-9, DS info), request/response timelines, storage location

- Issues Log & Opportunities Backlog — ranked list of waste, bottlenecks, and error types

Days 31-60 — "Recommend & Pilot"

Objectives

- Build a gap analysis (waste, rework, delays, risk).

- Propose to-be workflow with a minimal viable set of changes that reduces work for Jared/Jayson/Kendra

Deliverables

- Gap Analysis — top 10 issues with root causes and proposed fixes.

- Workflow Maps V1 — simplified swimlane + ownership; clearly mark what moves to Eva or other roles

- KPI/SLA Proposal — measure what matters (e.g., intake to setup lead time, clean handoff rate, defect rate at billing handoff, # of touches per job)

- Pilot Plan — choose 1-2 low-risk flows (e.g., dust permits, signage, pre-qual request packet) and run a 2-week pilot with baseline vs. after metrics

- Change Log — small incremental improvements enacted along the way (what/why/impact).

Standing Reviews (bi-weekly)

- Present 2-3 decisions needed, show expected impact, and request go/no-go.

- Keep pilots small, reversible, and documented.

Days 61-90 — "Launch & Operate To-Be v1"

Objectives

- Launch the to-be workflow v1 and enact KPI/SLAs.

- Establish a 30-day iteration rhythm (through Day 180).

Deliverables

- Operating Guide v1 — consolidated SOP pack, templates, and forms.

- RACI & Decision Rights

- KPI/SLA Dash (starter) — simple Monday/SharePoint tracker with weekly readout.

- Training & Handoffs — 60-minute walk-through for each stakeholder group; attendance logged.

- Iteration Plan — next 3 improvements with owners/dates.

Scope & Guardrails

- No billing/AR/portal ownership.

- Systems in scope: Monday.com, QuickBooks (read-only context), SharePoint/Notion, and any PM tooling Chi selects.

- Understand execution feeds (read-only learning):

  - SWPPP & Temp Fence: SWPPP Master File (Jayson).

  - Portable Toilets & Roll-Off: CRO is the execution system (Stephen/Wendy).

  - Water/Sweeping/other: Dawn's Master Billing File (Daniel/Kelley liaison).